## Instructions
Legal Disclaimer and Copyright
Disclaimer This guidance document has been prepared by National Grid Electricity System Operator Limited (NGESO) and is provided voluntarily and without charge. Whilst NGESO has taken all reasonable care in preparing this document, no representation or warranty either expressed or implied is made as to the accuracy or completeness of the information that it contains and parties using information within the document should make their own enquiries as to its accuracy and suitability for the purpose for which they use it. Neither NGESO nor any other companies in the National Grid plc group, nor any Directors or employees of any such company shall be liable for any error or misstatement or opinion on which the recipient of this document relies or seeks to rely other than fraudulent misstatement or fraudulent misrepresentation and does not accept any responsibility for any use which is made of the information or the document or (to the extent permitted by law) for any damages or losses incurred. In the event of any conflict or inconsistency between this document and the Capacity Market Rules, the Electricity Capacity Regulations or the Auction Guidelines, the latter documents take precedence. Capitalised terms used in this document shall have the same meanings given in the Capacity Market Rules. | Milestone List tab A number of pre-set slicers have been added to this tab to aid selection of milestones Coronavirus Easements This tab set out the impact on milestones in Respect of the Effects of Coronavirus (CM Rules Chapter 18) and should be reviewed in conjunction with the main milestone list tab. 1.) Extended Long-Stop Date Please note, the following deadlines are conditional based on meeting the eligibility requirements described in Rule 6.7.4A within Chapter 18 of the Capacity Market Rules. They are only applicable to those CMUs that have received Delivery Body approval following submission of an ITE report by September 30th 2021. Those with a 2015 (T-4) Agreement will automatically have their Longstop date extended to the 30 September 2022 providing an ITE report was provided and approved before the 30 September 2020. 2.) Extended DSR Test or Metering Test Please note, the following deadlines are conditional based on meeting the eligibility requirements described in Rule 8.3.2ZA within Chapter 18 of the Capacity Market Rules. They are only applicable to those CMUs that have received Delivery Body approval following submission of an ITE report by August 31st 2022.
Confidentiality This guidance document, and its contents should be considered as confidential in nature, and this document is supplied on this basis. No part of this document may be reproduced in any material form (including photocopying and restoring in any medium or electronic means and whether or not transiently or incidentally) without the written permission of NGESO.
Copyright National Grid 2021, all rights reserved.

## Amendment History
Date of change | Detail of changes made
2022-11-03 | Change Credit Cover deadline for CMUs that receive a Conditonally Prequalified Status following Tier1 Disputes.
2022-10-19 | Added additional deadline dates for Construction Reports (New Build and Refurbishing): T-4 (2026 DY) All Milestone Dates T-3 (2022 DY) Milestone Dates 6 and 7 - NB and Refurb T-4 (2023 DY) Milestone Dates 6 and 7 - NB and Refurb T-4 (2024 DY) Milestone Dates 4, 5, 6 and 7 - NB and Refurb
Added 2022 Credit Cover Deadlines
Updated DSR Test and Reallocation Deadlines
Inserted extra line at 471 to add missing T-4 Refurbishing deadline for TPS now deleted again as it was there but line was minimised
Updated all Longstop dates for SCM T-3 & T-4
Old SCM Refurb deadline for T-4 2020 was showing incorrectly as 01/10/2020 when it should have been 01/10/2021
Addition of FCM for 2026 DY
Emissions Deadlines for Agreements applied for in the 2022 PQ process added
Metering Asessment & Metering Test Certificate Deadlines for Agreements applied for in the 2022 PQ process added
Clarified Metering Long Stop deadlines with regards to prospective CMUs are the latest date to provide. If an Agreement is to take effect at the earliest possible time then Metering Assessment (and where applicable Test Certificate) must be provided by Delivery Year start as part of the Substantial Completion Milestone.
Addition of suspend and recoup rows (wish to reflect T4 2016s (2020s) multi years having the September deadline) and amended name to incorporate 'Auction 2016 and prior' for clarity Addition of T4 2026s for suspensions and terminations
Added TPS 2026 DY
Added EYC 2026 DY
Emissions Pre-refurb deadlines updated to include provisional Auction Results Day
Added connection agreement dates for DY 2026/2027
2022-05-16 | Unproven DSR Metering Assessment Deadline removed as not defined under Rule 8.3.3
2022-04-06 | Added SPDs, Suspend and Recoup T-4 2020 - Refurbishing type
2022-04-04 | SCM updated for T-1 2022 Newbuild and Refurbishment
2022-03-04 | Amendments to the T-4 (2025 DY) Emissions and FCM deadlines based on revised Auction Results Day Amendments to the T-1 (2022 DY) Emissions deadlines based on revised Auction Results Day Added additional deadlines for T-4 (2025 DY) for SPDs Added long stop date for T-1 2021 Auction Added 2025 and 2026 DY deadlines for EYC, Capex and SCM Removed DY 2023 and 2024 T-1 SPD dates (in case of future rule changes) Corrected auction years for TPS to T-4 Added connection agreement dates for DY 2025/2026
2022-02-18 | Update the 2022/23 delivery year T-1 FCM deadlines following confirmation of the Auction Results Day from 28th May 2022 to 25th May 2022
2021-12-09 | Added Prequalification deadline - Planning Consents, Confirmation of Entry Close.
2021-11-09 | Add Credit Cover Deadlines following Tier1 and Tier 2 Disputes
2021-09-07 | Added additional deadline dates for all Auctions of Construction reports (New Build and Refurbishing): T-4 2017 T-3 2019 T-4 2019 T-4 2020 T-4 2021
2021-09-07 | Changed the date for Extended Years from 1st October to the 1st Jan of the 1st Delivery Year following new 2021 Rule changes
2021-09-07 | Fossil Fuel Emissions Milestones added for: T-4 2025 DY T-1 2022 DY
2021-09-07 | Added additional deadlines for DSR Tests and Credit Cover
2021-09-07 | Additional deadlines for T-4 SPDs (terminations and suspensions) and addition of Refurbishing CMU deadlines for all T-1s and T-4s
2021-09-07 | Meter Assessment & Meter Test Cert T-4 Refurbishing Longstop Date for historic agreements updated to reflect new Longstop definition of being 12 months post DY start in line with New Builds. (RS 03/09/21)
2021-09-07 | Updated to Credit Cover dates. Added FCM deadlines - subject to change on Auction Results Day.
2021-07-05 | Updates to SCM refurbishing CMU's and Easements following Summer 2021 Rules changes and removed milestones that have passed or no longer being carried forward as part of the 2021 Easement arrangements.
2021-06-11 | Update to the SCM milestone for T1 New Build from Oct 20 to Oct 21

## Milestone list
Deadline Name | Auction type | Generating CMU Type | Delivery Year | Deadline Date | Year of deadline | Month of deadline
Component Reallocation - Addition | T-1 | Proven DSR | 2020 | 2021-07-31 | 2021 | Jul
Component Reallocation - Addition | T-1 | Proven DSR | 2021 | 2022-07-31 | 2022 | Jul
Component Reallocation - Addition | T-1 | Proven DSR | 2022 | 2023-07-31 | 2023 | Jul
Component Reallocation - Addition | T-1 | Proven DSR | 2023 | 2024-07-31 | 2024 | Jul
Component Reallocation - Addition | T-1 | Proven DSR | 2024 | 2025-07-31 | 2025 | Jul
Component Reallocation - Addition | T-4 | Proven DSR | 2020 | 2021-07-31 | 2021 | Jul
Component Reallocation - Addition | T-4 | Proven DSR | 2021 | 2022-07-31 | 2022 | Jul
Component Reallocation - Addition | T-4 | Proven DSR | 2022 | 2023-07-31 | 2023 | Jul
Component Reallocation - Addition | T-4 | Proven DSR | 2023 | 2024-07-31 | 2024 | Jul
Component Reallocation - Addition | T-4 | Proven DSR | 2024 | 2025-07-31 | 2025 | Jul
Component Reallocation - Addition | T-4 | Proven DSR | 2025 | 2026-07-31 | 2026 | Jul
Component Reallocation - Addition | T-4 | Proven DSR | 2026 | 2027-07-31 | 2027 | Jul
Component Reallocation - DSR Test | T-1 | Proven DSR | 2020 | 2021-08-31 | 2021 | Aug
Component Reallocation - DSR Test | T-1 | Proven DSR | 2021 | 2022-08-31 | 2022 | Aug
Component Reallocation - DSR Test | T-1 | Proven DSR | 2022 | 2023-08-31 | 2023 | Aug
Component Reallocation - DSR Test | T-1 | Proven DSR | 2023 | 2024-08-31 | 2024 | Aug
Component Reallocation - DSR Test | T-1 | Proven DSR | 2024 | 2025-08-31 | 2025 | Aug
Component Reallocation - DSR Test | T-4 | Proven DSR | 2020 | 2021-08-31 | 2021 | Aug
Component Reallocation - DSR Test | T-4 | Proven DSR | 2021 | 2022-08-31 | 2022 | Aug
Component Reallocation - DSR Test | T-4 | Proven DSR | 2022 | 2023-08-31 | 2023 | Aug
Component Reallocation - DSR Test | T-4 | Proven DSR | 2023 | 2024-08-31 | 2024 | Aug
Component Reallocation - DSR Test | T-4 | Proven DSR | 2024 | 2025-08-31 | 2025 | Aug
Component Reallocation - DSR Test | T-4 | Proven DSR | 2025 | 2026-08-31 | 2026 | Aug
Component Reallocation - DSR Test | T-4 | Proven DSR | 2026 | 2027-08-31 | 2027 | Aug
Confirmation of Entry | T-4 | Unproven DSR | 2025 | 2022-02-08 | 2022 | Feb
Confirmation of Entry | T-4 | New Build | 2025 | 2022-02-08 | 2022 | Feb
Confirmation of Entry | T-4 | Refurbishing | 2025 | 2022-02-08 | 2022 | Feb
Confirmation of Entry | T-4 | Prospective Interconnector | 2025 | 2022-02-08 | 2022 | Feb
Confirmation of Entry | T-4 | Proven DSR | 2025 | 2022-02-08 | 2022 | Feb
Confirmation of Entry | T-1 | Unproven DSR | 2022 | 2022-02-01 | 2022 | Feb
Confirmation of Entry | T-1 | New Build | 2022 | 2022-02-01 | 2022 | Feb
Confirmation of Entry | T-1 | Refurbishing | 2022 | 2022-02-01 | 2022 | Feb
Confirmation of Entry | T-1 | Prospective Interconnector | 2022 | 2022-02-01 | 2022 | Feb
Confirmation of Entry | T-1 | Proven DSR | 2022 | 2022-02-01 | 2022 | Feb
Connection Agreement (Distribution only) | T-4 | New Build | 2023 | 2022-03-31 | 2022 | Mar
Connection Agreement (Distribution only) | T-4 | New Build | 2024 | 2023-03-31 | 2023 | Mar
Connection Agreement (Distribution only) | T-4 | New Build | 2025 | 2024-03-31 | 2024 | Mar
Connection Agreement (Distribution only) | T-4 | New Build | 2026 | 2025-03-31 | 2025 | Mar
Connection Agreement (Distribution only) | T-4 | New Build | 2027 | 2026-03-31 | 2026 | Mar
Credit Cover | T-1 | New Build | 2023 | 2022-11-21 | 2022 | Nov
Credit Cover | T-4 | New Build | 2026 | 2022-11-21 | 2022 | Nov
Credit Cover | T-1 | Unproven DSR | 2023 | 2022-11-21 | 2022 | Nov
Credit Cover | T-4 | Unproven DSR | 2026 | 2022-11-21 | 2022 | Nov
Credit Cover (Following Tier1 Disputes) | T-1 | New Build | 2023 | 2022-12-20 | 2022 | Dec
Credit Cover (Following Tier1 Disputes) | T-4 | New Build | 2026 | 2022-12-20 | 2022 | Dec
Credit Cover (Following Tier1 Disputes) | T-1 | Unproven DSR | 2023 | 2022-12-20 | 2022 | Dec
Credit Cover (Following Tier1 Disputes) | T-4 | Unproven DSR | 2026 | 2022-12-20 | 2022 | Dec
Credit Cover (Following Tier2 Disputes) | T-1 | New Build | 2023 | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision
Credit Cover (Following Tier2 Disputes) | T-4 | New Build | 2026 | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision
Credit Cover (Following Tier2 Disputes) | T-1 | Unproven DSR | 2023 | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision
Credit Cover (Following Tier2 Disputes) | T-4 | Unproven DSR | 2026 | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision | 15 Working Days after Tier 2 Dispute Decision
DSR Test - Multi Year Agreement | T-4 | Unproven DSR | 2024 | 2024-10-01 | 2024 | Oct
DSR Test - Multi Year Agreement | T-4 | Unproven DSR | 2025 | 2025-10-01 | 2025 | Oct
DSR Test - Multi Year Agreement | T-4 | Unproven DSR | 2026 | 2026-10-01 | 2026 | Oct
DSR Test - Single Year Agreement | T-1 | Unproven DSR | 2021 | 2021-08-31 | 2021 | Aug
DSR Test - Single Year Agreement | T-1 | Unproven DSR | 2022 | 2022-08-31 | 2022 | Aug
DSR Test - Single Year Agreement | T-1 | Unproven DSR | 2023 | 2023-08-31 | 2023 | Aug
DSR Test - Single Year Agreement | T-1 | Unproven DSR | 2024 | 2024-08-31 | 2024 | Aug
DSR Test - Single Year Agreement | T-3 | Unproven DSR | 2022 | 2022-08-31 | 2022 | Aug
DSR Test - Single Year Agreement | T-4 | Unproven DSR | 2021 | 2021-08-31 | 2021 | Aug
DSR Test - Single Year Agreement | T-4 | Unproven DSR | 2022 | 2022-08-31 | 2022 | Aug
DSR Test - Single Year Agreement | T-4 | Unproven DSR | 2023 | 2023-08-31 | 2023 | Aug
DSR Test - Single Year Agreement | T-4 | Unproven DSR | 2024 | 2024-08-31 | 2024 | Aug
DSR Test - Single Year Agreement | T-1 | Unproven DSR | 2022 | 2022-08-31 | 2022 | Aug
DSR Test - Single Year Agreement | T-4 | Unproven DSR | 2025 | 2025-08-31 | 2025 | Aug
DSR Test - Single Year Agreement | T-1 | Unproven DSR | 2023 | 2023-08-31 | 2023 | Aug
DSR Test - Single Year Agreement | T-4 | Unproven DSR | 2026 | 2026-08-31 | 2026 | Aug
Emissions Declaration (standard formula used) | T-1 | New Build | 2021 | 2021-10-01 | 2021 | Oct
Emissions Declaration (standard formula used) | T-1 | Refurbishing | 2021 | 2021-10-01 | 2021 | Oct
Emissions Declaration (standard formula used) | T-1 | Pre-Refurb | 2021 | 2021-05-12 | 2021 | May
Emissions Declaration (standard formula used) | T-4 | Refurbishing | 2024 | 01/10/2024 (or Agreement start) | 2024 | Oct
Emissions Declaration (standard formula used) | T-4 | Unproven DSR | 2024 | With DSR Test | n/a | n/a
Emissions Declaration (standard formula used) | T-1 | Unproven DSR | 2021 | With DSR Test | n/a | n/a
Emissions Declaration (standard formula used) | T-4 | Pre-Refurb | 2024 | 2021-05-22 | 2021 | May
Emissions Declaration (standard formula used) | T-4 | New Build | 2024 | 01/10/2024 (or Agreement start) | 2024 | Oct
Emissions Declaration (standard formula used) | T-4 | New Build | 2025 | 01/10/2025 (or Agreement start) | 2025 | Oct
Emissions Declaration (standard formula used) | T-4 | Refurbishing | 2025 | 01/10/2025 (or Agreement start) | 2025 | Oct
Emissions Declaration (standard formula used) | T-4 | Pre-Refurb | 2025 | 2022-05-04 | 2022 | May
Emissions Declaration (standard formula used) | T-4 | Unproven DSR | 2025 | With DSR Test | n/a | n/a
Emissions Declaration (standard formula used) | T-1 | New Build | 2022 | 2022-10-01 | 2022 | Oct
Emissions Declaration (standard formula used) | T-1 | Refurbishing | 2022 | 2022-10-01 | 2022 | Oct
Emissions Declaration (standard formula used) | T-1 | Pre-Refurb | 2022 | 2022-04-25 | 2022 | Apr
Emissions Declaration (standard formula used) | T-1 | Unproven DSR | 2022 | With DSR Test | n/a | n/a
Emissions Declaration (standard formula used) | T-4 | New Build | 2026 | 01/10/2026 (or Agreement start) | 2026 | Oct
Emissions Declaration (standard formula used) | T-4 | Refurbishing | 2026 | 01/10/2026 (or Agreement start) | 2026 | Oct
Emissions Declaration (standard formula used) | T-4 | Pre-Refurb | 2026 | 2023-05-03 | 2023 | May
Emissions Declaration (standard formula used) | T-4 | Unproven DSR | 2026 | With DSR Test | n/a | n/a
Emissions Declaration (standard formula used) | T-1 | New Build | 2023 | 2023-10-01 | 2023 | Oct
Emissions Declaration (standard formula used) | T-1 | Refurbishing | 2023 | 2023-10-01 | 2023 | Oct
Emissions Declaration (standard formula used) | T-1 | Pre-Refurb | 2023 | 2023-04-24 | 2023 | Apr
Emissions Declaration (standard formula used) | T-1 | Unproven DSR | 2023 | With DSR Test | n/a | n/a
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | New Build | 2025 | 01/12/2026 (or 14 months after Agreement start) | 2026 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Refurbishing | 2025 | 01/12/2026 (or 14 months after Agreement start) | 2026 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Unproven DSR | 2025 | 01/12/2026 (or Agreement start) | 2026 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Pre-Refurb | 2025 | 01/12/2026 (or Agreement start) | 2026 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Existing Generating | 2025 | 01/12/2026 (or Agreement start) | 2026 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Proven DSR | 2025 | 01/12/2026 (or Agreement start) | 2026 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | New Build | 2026 | 01/12/2027 (or 14 months after Agreement start) | 2027 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Refurbishing | 2026 | 01/12/2027 (or 14 months after Agreement start) | 2027 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Unproven DSR | 2026 | 01/12/2027 (or 14 months after Agreement start) | 2027 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Pre-Refurb | 2026 | 01/12/2027 (or 14 months after Agreement start) | 2027 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Existing Generating | 2026 | 01/12/2027 (or 14 months after Agreement start) | 2027 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-4 | Proven DSR | 2026 | 01/12/2027 (or 14 months after Agreement start) | 2027 | Dec
Emissions Declaration (CHPQA Formulae used) | T-4 | New Build | 2025 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Refurbishing | 2025 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Unproven DSR | 2025 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Pre-Refurb | 2025 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Existing Generating | 2025 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Proven DSR | 2025 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | New Build | 2026 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Refurbishing | 2026 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Unproven DSR | 2026 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Pre-Refurb | 2026 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Existing Generating | 2026 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-4 | Proven DSR | 2026 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | New Build | 2022 | 2023-12-01 | 2023 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Refurbishing | 2022 | 2023-12-01 | 2023 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Unproven DSR | 2022 | 2023-12-01 | 2023 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Pre-Refurb | 2022 | 2023-12-01 | 2023 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Existing Generating | 2022 | 2023-12-01 | 2023 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Proven DSR | 2022 | 2023-12-01 | 2023 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | New Build | 2023 | 2024-12-01 | 2024 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Refurbishing | 2023 | 2024-12-01 | 2024 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Unproven DSR | 2023 | 2024-12-01 | 2024 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Pre-Refurb | 2023 | 2024-12-01 | 2024 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Existing Generating | 2023 | 2024-12-01 | 2024 | Dec
Emissions Declaration (CCUS and/or Mixed Fuels Formulae used) | T-1 | Proven DSR | 2023 | 2024-12-01 | 2024 | Dec
Emissions Declaration (CHPQA Formulae used) | T-1 | New Build | 2022 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Refurbishing | 2022 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Unproven DSR | 2022 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Pre-Refurb | 2022 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Existing Generating | 2022 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Proven DSR | 2022 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | New Build | 2023 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Refurbishing | 2023 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Unproven DSR | 2023 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Pre-Refurb | 2023 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Existing Generating | 2023 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Emissions Declaration (CHPQA Formulae used) | T-1 | Proven DSR | 2023 | Prior to Sep following CHPQA Cal Yr. | n/a | Aug
Extended Years Criteria | T-3 | New Build | 2022 | 2023-01-01 | 2023 | Jan
Extended Years Criteria | T-4 | New Build | 2021 | 2022-01-01 | 2022 | Jan
Extended Years Criteria | T-4 | New Build | 2023 | 2024-01-01 | 2024 | Jan
Extended Years Criteria | T-4 | New Build | 2024 | 2025-01-01 | 2025 | Jan
Extended Years Criteria | T-4 | New Build | 2025 | 2026-01-01 | 2026 | Jan
Extended Years Criteria | T-4 | New Build | 2026 | 2027-01-01 | 2027 | Jan
Financial Commitment Milestone | T-1 | New Build | 2021 | 2021-06-12 | 2021 | Jun
Financial Commitment Milestone | T-1 | Refurbishing | 2021 | 2021-06-12 | 2021 | Jun
Financial Commitment Milestone | T-1 | Prospective Interconnector | 2021 | 2021-06-12 | 2021 | Jun
Financial Commitment Milestone | T-1 | New Build | 2022 | 2022-05-25 | 2022 | May
Financial Commitment Milestone | T-1 | Refurbishing | 2022 | 2022-05-25 | 2022 | May
Financial Commitment Milestone | T-1 | Prospective Interconnector | 2022 | 2022-05-25 | 2022 | May
Financial Commitment Milestone- 11 Month Deadline | T-3 | New Build | 2022 | 2021-01-12 | 2021 | Jan
Financial Commitment Milestone- 11 Month Deadline | T-3 | Prospective Interconnector | 2022 | 2021-01-12 | 2021 | Jan
Financial Commitment Milestone- 11 Month Deadline | T-4 | New Build | 2023 | 2021-02-18 | 2021 | Feb
Financial Commitment Milestone- 11 Month Deadline | T-4 | Prospective Interconnector | 2023 | 2021-02-18 | 2021 | Feb
Financial Commitment Milestone- 12 Month Deadline | T-4 | New Build | 2023 | 2021-03-18 | 2021 | Mar
Financial Commitment Milestone- 12 Month Deadline | T-4 | Prospective Interconnector | 2023 | 2021-03-18 | 2021 | Mar
Financial Commitment Milestone- 16 Month Deadline | T-4 | New Build | 2023 | 2021-07-18 | 2021 | Jul
Financial Commitment Milestone- 16 Month Deadline | T-4 | Refurbishing | 2023 | 2021-07-18 | 2021 | Jul
Financial Commitment Milestone- 12 Month Deadline | T-3 | New Build | 2022 | 2021-02-12 | 2021 | Feb
Financial Commitment Milestone- 12 Month Deadline | T-3 | Prospective Interconnector | 2022 | 2021-02-12 | 2021 | Feb
Financial Commitment Milestone- 16 Month Deadline | T-4 | Prospective Interconnector | 2023 | 2021-07-18 | 2021 | Jul
Financial Commitment Milestone- 11 Month Deadline | T-4 | Prospective Interconnector | 2024 | 2022-02-22 | 2022 | Feb
Financial Commitment Milestone- 11 Month Deadline | T-4 | New Build | 2024 | 2022-02-22 | 2022 | Feb
Financial Commitment Milestone- 12 Month Deadline | T-4 | New Build | 2024 | 2022-03-22 | 2022 | Mar
Financial Commitment Milestone- 12 Month Deadline | T-4 | Prospective Interconnector | 2024 | 2022-03-22 | 2022 | Mar
Financial Commitment Milestone- 16 Month Deadline | T-4 | Prospective Interconnector | 2024 | 2022-07-22 | 2022 | Jul
Financial Commitment Milestone- 16 Month Deadline | T-3 | New Build | 2022 | 2021-06-12 | 2021 | Jun
Financial Commitment Milestone- 16 Month Deadline | T-3 | Refurbishing | 2022 | 2021-06-12 | 2021 | Jun
Financial Commitment Milestone- 16 Month Deadline | T-3 | Prospective Interconnector | 2022 | 2021-06-12 | 2021 | Jun
Financial Commitment Milestone- 16 Month Deadline | T-4 | Refurbishing | 2024 | 2022-07-22 | 2022 | Jul
Financial Commitment Milestone- 16 Month Deadline | T-4 | New Build | 2024 | 2022-07-22 | 2022 | Jul
Financial Commitment Milestone- 11 Month Deadline | T-4 | New Build | 2025 | 2023-02-04 | 2023 | Feb
Financial Commitment Milestone- 11 Month Deadline | T-4 | Prospective Interconnector | 2025 | 2023-02-04 | 2023 | Feb
Financial Commitment Milestone- 12 Month Deadline | T-4 | New Build | 2025 | 2023-03-04 | 2023 | Mar
Financial Commitment Milestone- 12 Month Deadline | T-4 | Prospective Interconnector | 2025 | 2023-03-04 | 2023 | Mar
Financial Commitment Milestone- 16 Month Deadline | T-4 | Prospective Interconnector | 2025 | 2023-07-04 | 2023 | Jul
Financial Commitment Milestone- 16 Month Deadline | T-4 | Refurbishing | 2025 | 2023-07-04 | 2023 | Jul
Financial Commitment Milestone- 16 Month Deadline | T-4 | New Build | 2025 | 2023-07-04 | 2023 | Jul
Financial Commitment Milestone- 11 Month Deadline | T-4 | New Build | 2026 | 2024-02-03 | 2024 | Feb
Financial Commitment Milestone- 11 Month Deadline | T-4 | Prospective Interconnector | 2026 | 2024-02-03 | 2024 | Feb
Financial Commitment Milestone- 12 Month Deadline | T-4 | New Build | 2026 | 2024-03-03 | 2024 | Mar
Financial Commitment Milestone- 12 Month Deadline | T-4 | Prospective Interconnector | 2026 | 2024-03-03 | 2024 | Mar
Financial Commitment Milestone- 16 Month Deadline | T-4 | Prospective Interconnector | 2026 | 2024-07-03 | 2024 | Jul
Financial Commitment Milestone- 16 Month Deadline | T-4 | Refurbishing | 2026 | 2024-07-03 | 2024 | Jul
Financial Commitment Milestone- 16 Month Deadline | T-4 | New Build | 2026 | 2024-07-03 | 2024 | Jul
Long Stop Date | T-4 | New Build | 2020 | 2021-10-01 | 2021 | Oct
Long Stop Date | T-4 | Refurbishing | 2020 | 2021-10-01 | 2021 | Oct
Long Stop Date | T-4 | New Build | 2021 | 2022-10-01 | 2022 | Oct
Long Stop Date | T-4 | Refurbishing | 2021 | 2022-10-01 | 2022 | Oct
Long Stop Date | T-3 | New Build | 2022 | 2023-10-01 | 2023 | Oct
Long Stop Date | T-3 | Refurbishing | 2022 | 2023-10-01 | 2023 | Oct
Long Stop Date | T-4 | New Build | 2023 | 2024-10-01 | 2024 | Oct
Long Stop Date | T-4 | Refurbishing | 2023 | 2024-10-01 | 2024 | Oct
Long Stop Date | T-4 | New Build | 2024 | 2025-10-01 | 2025 | Oct
Long Stop Date | T-4 | Refurbishing | 2024 | 2025-10-01 | 2025 | Oct
Long Stop Date | T-4 | New Build | 2025 | 2026-10-01 | 2026 | Oct
Long Stop Date | T-4 | Refurbishing | 2025 | 2026-10-01 | 2026 | Oct
Long Stop Date | T-4 | New Build | 2026 | 2027-10-01 | 2027 | Oct
Long Stop Date | T-4 | Refurbishing | 2026 | 2027-10-01 | 2027 | Oct
Metering Assessment | T-1 | Existing Generating | 2021 | 2021-07-02 | 2021 | Jul
Metering Assessment | T-1 | Proven DSR | 2021 | 2021-07-02 | 2021 | Jul
Metering Assessment | T-1 | New Build | 2021 | 2021-10-01 | 2021 | Oct
Metering Assessment | T-1 | Refurbishing | 2021 | 2021-10-01 | 2021 | Oct
Metering Assessment | T-1 | Prospective Interconnector | 2021 | 2021-10-01 | 2021 | Oct
Metering Assessment | T-1 | Existing Interconnector | 2021 | 2021-07-02 | 2021 | Jul
Metering Assessment | T-3 | New Build | 2022 | 01/10/2023 (latest - provide by DY start to meet SCM) | 2023 | Oct
Metering Assessment | T-3 | Existing Generating | 2022 | 2020-10-01 | 2020 | Oct
Metering Assessment | T-3 | Proven DSR | 2022 | 2020-10-01 | 2020 | Oct
Metering Assessment | T-3 | Existing Interconnector | 2022 | 2020-10-01 | 2020 | Oct
Metering Assessment | T-3 | Prospective Interconnector | 2022 | 01/10/2023 (latest - provide by DY start to meet SCM) | 2023 | Oct
Metering Assessment | T-3 | Refurbishing | 2022 | 01/10/2023 (latest - provide by DY start to meet SCM) | 2023 | Oct
Metering Assessment | T-4 | New Build | 2020 | 01/10/2021 (latest - provide by DY start to meet SCM) | 2021 | Oct
Metering Assessment | T-4 | Prospective Interconnector | 2020 | 01/10/2021 (latest - provide by DY start to meet SCM) | 2021 | Oct
Metering Assessment | T-4 | Refurbishing | 2021 | 01/10/2022 (latest - provide by DY start to meet SCM) | 2022 | Oct
Metering Assessment | T-4 | New Build | 2021 | 01/10/2022 (latest - provide by DY start to meet SCM) | 2022 | Oct
Metering Assessment | T-4 | Prospective Interconnector | 2021 | 01/10/2022 (latest - provide by DY start to meet SCM) | 2022 | Oct
Metering Assessment | T-4 | Existing Generating | 2023 | 2020-10-01 | 2020 | Oct
Metering Assessment | T-4 | Proven DSR | 2023 | 2020-10-01 | 2020 | Oct
Metering Assessment | T-4 | Existing Interconnector | 2023 | 2020-10-01 | 2020 | Oct
Metering Assessment | T-4 | New Build | 2023 | 01/10/2024 (latest - provide by DY start to meet SCM) | 2024 | Oct
Metering Assessment | T-4 | Prospective Interconnector | 2023 | 01/10/2024 (latest - provide by DY start to meet SCM) | 2024 | Oct
Metering Assessment | T-4 | Refurbishing | 2023 | 01/10/2024 (latest - provide by DY start to meet SCM) | 2024 | Oct
Metering Assessment | T-4 | Existing Generating | 2024 | 2021-10-01 | 2021 | Oct
Metering Assessment | T-4 | Proven DSR | 2024 | 2021-10-01 | 2021 | Oct
Metering Assessment | T-4 | Existing Interconnector | 2024 | 2021-10-01 | 2021 | Oct
Metering Assessment | T-4 | New Build | 2024 | 01/10/2025 (latest - provide by DY start to meet SCM) | 2025 | Oct
Metering Assessment | T-4 | Prospective Interconnector | 2024 | 01/10/2025 (latest - provide by DY start to meet SCM) | 2025 | Oct
Metering Assessment | T-4 | Refurbishing | 2024 | 01/10/2025 (latest - provide by DY start to meet SCM) | 2025 | Oct
Metering Assessment | T-4 | Existing Generating | 2025 | 2022-10-01 | 2022 | Oct
Metering Assessment | T-4 | Proven DSR | 2025 | 2022-10-01 | 2022 | Oct
Metering Assessment | T-4 | Existing Interconnector | 2025 | 2022-10-01 | 2022 | Oct
Metering Assessment | T-4 | New Build | 2025 | 01/10/2026 (latest - provide by DY start to meet SCM) | 2026 | Oct
Metering Assessment | T-4 | Prospective Interconnector | 2025 | 01/10/2026 (latest - provide by DY start to meet SCM) | 2026 | Oct
Metering Assessment | T-4 | Refurbishing | 2025 | 01/10/2026 (latest - provide by DY start to meet SCM) | 2026 | Oct
Metering Assessment | T-4 | Existing Generating | 2026 | 2023-10-01 | 2023 | Oct
Metering Assessment | T-4 | Proven DSR | 2026 | 2023-10-01 | 2023 | Oct
Metering Assessment | T-4 | Existing Interconnector | 2026 | 2023-10-01 | 2023 | Oct
Metering Assessment | T-4 | New Build | 2026 | 01/10/2027 (latest - provide by DY start to meet SCM) | 2027 | Oct
Metering Assessment | T-4 | Prospective Interconnector | 2026 | 01/10/2027 (latest - provide by DY start to meet SCM) | 2027 | Oct
Metering Assessment | T-4 | Refurbishing | 2026 | 01/10/2027 (latest - provide by DY start to meet SCM) | 2027 | Oct
Metering Assessment | T-1 | Existing Generating | 2022 | 2022-06-16 | 2022 | Jun
Metering Assessment | T-1 | Proven DSR | 2022 | 2022-06-16 | 2022 | Jun
Metering Assessment | T-1 | Existing Interconnector | 2022 | 2022-06-16 | 2022 | Jun
Metering Assessment | T-1 | New Build | 2022 | 2022-10-01 | 2022 | Oct
Metering Assessment | T-1 | Prospective Interconnector | 2022 | 2022-10-01 | 2022 | Oct
Metering Assessment | T-1 | Refurbishing | 2022 | 2022-10-01 | 2022 | Oct
Metering Assessment | T-1 | Existing Generating | 2023 | 2023-06-14 | 2023 | Jun
Metering Assessment | T-1 | Proven DSR | 2023 | 2023-06-14 | 2023 | Jun
Metering Assessment | T-1 | Existing Interconnector | 2023 | 2023-06-14 | 2023 | Jun
Metering Assessment | T-1 | New Build | 2023 | 2023-10-01 | 2023 | Oct
Metering Assessment | T-1 | Prospective Interconnector | 2023 | 2023-10-01 | 2023 | Oct
Metering Assessment | T-1 | Refurbishing | 2023 | 2023-10-01 | 2023 | Oct
Metering Test | T-1 | Existing Generating | 2021 | 2021-09-17 | 2021 | Sep
Metering Test | T-1 | Existing Interconnector | 2021 | 2021-09-17 | 2021 | Sep
Metering Test | T-1 | New Build | 2021 | 2021-10-01 | 2021 | Oct
Metering Test | T-1 | Prospective Interconnector | 2021 | 2021-10-01 | 2021 | Oct
Metering Test | T-1 | Unproven DSR | 2021 | 2021-09-17 | 2021 | Sep
Metering Test | T-1 | Proven DSR | 2021 | 2021-09-17 | 2021 | Sep
Metering Test | T-1 | Refurbishing | 2021 | 2021-10-01 | 2021 | Oct
Metering Test | T-3 | New Build | 2022 | 01/10/2023 (latest - provide by DY start to meet SCM) | 2023 | Oct
Metering Test | T-3 | Existing Generating | 2022 | 2021-03-31 | 2021 | Mar
Metering Test | T-3 | Proven DSR | 2022 | 2021-03-31 | 2021 | Mar
Metering Test | T-3 | Existing Interconnector | 2022 | 2021-03-31 | 2021 | Mar
Metering Test | T-3 | Unproven DSR | 2022 | 2022-09-17 | 2022 | Sep
Metering Test | T-3 | Prospective Interconnector | 2022 | 01/10/2023 (latest - provide by DY start to meet SCM) | 2023 | Oct
Metering Test | T-3 | Refurbishing | 2022 | 01/10/2023 (latest - provide by DY start to meet SCM) | 2023 | Oct
Metering Test | T-4 | New Build | 2020 | 01/10/2021 (latest - provide by DY start to meet SCM) | 2021 | Oct
Metering Test | T-4 | Refurbishing | 2020 | 01/10/2020 (latest - provide by DY start to meet SCM) | 2020 | Oct
Metering Test | T-4 | Prospective Interconnector | 2020 | 01/10/2021 (latest - provide by DY start to meet SCM) | 2021 | Oct
Metering Test | T-4 | New Build | 2021 | 01/10/2022 (latest - provide by DY start to meet SCM) | 2022 | Oct
Metering Test | T-4 | Refurbishing | 2021 | 01/10/2022 (latest - provide by DY start to meet SCM) | 2022 | Oct
Metering Test | T-4 | Prospective Interconnector | 2021 | 01/10/2022 (latest - provide by DY start to meet SCM) | 2022 | Oct
Metering Test | T-4 | Unproven DSR | 2021 | 2021-09-17 | 2021 | Sep
Metering Test | T-4 | New Build | 2023 | 01/10/2024 (latest - provide by DY start to meet SCM) | 2024 | Oct
Metering Test | T-4 | Existing Interconnector | 2023 | 2022-03-31 | 2022 | Mar
Metering Test | T-4 | Existing Generating | 2023 | 2022-03-31 | 2022 | Mar
Metering Test | T-4 | Proven DSR | 2023 | 2022-03-31 | 2022 | Mar
Metering Test | T-4 | Unproven DSR | 2023 | 2023-09-17 | 2023 | Sep
Metering Test | T-4 | Refurbishing | 2023 | 01/10/2024 (latest - provide by DY start to meet SCM) | 2024 | Oct
Metering Test | T-4 | Prospective Interconnector | 2023 | 01/10/2024 (latest - provide by DY start to meet SCM) | 2024 | Oct
Metering Test | T-4 | New Build | 2024 | 01/10/2025 (latest - provide by DY start to meet SCM) | 2025 | Oct
Metering Test | T-4 | Existing Interconnector | 2024 | 2023-03-31 | 2023 | Mar
Metering Test | T-4 | Existing Generating | 2024 | 2023-03-31 | 2023 | Mar
Metering Test | T-4 | Proven DSR | 2024 | 2023-03-31 | 2023 | Mar
Metering Test | T-4 | Unproven DSR | 2024 | 2024-09-17 | 2024 | Sep
Metering Test | T-4 | Refurbishing | 2024 | 01/10/2025 (latest - provide by DY start to meet SCM) | 2025 | Oct
Metering Test | T-4 | Prospective Interconnector | 2024 | 01/10/2025 (latest - provide by DY start to meet SCM) | 2025 | Oct
Metering Test (With Multi-year Agreement) | T-4 | Unproven DSR | 2024 | 2025-09-17 | 2025 | Sep
Metering Test | T-4 | New Build | 2025 | 01/10/2026 (latest - provide by DY start to meet SCM) | 2026 | Oct
Metering Test | T-4 | Existing Interconnector | 2025 | 2024-03-31 | 2024 | Mar
Metering Test | T-4 | Existing Generating | 2025 | 2024-03-31 | 2024 | Mar
Metering Test | T-4 | Proven DSR | 2025 | 2024-03-31 | 2024 | Mar
Metering Test | T-4 | Unproven DSR | 2025 | 2025-09-17 | 2025 | Sep
Metering Test | T-4 | Refurbishing | 2025 | 01/10/2026 (latest - provide by DY start to meet SCM) | 2026 | Oct
Metering Test | T-4 | Prospective Interconnector | 2025 | 01/10/2026 (latest - provide by DY start to meet SCM) | 2026 | Oct
Metering Test (With Multi-year Agreement) | T-4 | Unproven DSR | 2025 | 2026-09-17 | 2026 | Sep
Metering Test | T-4 | New Build | 2026 | 01/10/2027 (latest - provide by DY start to meet SCM) | 2027 | Oct
Metering Test | T-4 | Existing Interconnector | 2026 | 2025-03-31 | 2025 | Mar
Metering Test | T-4 | Existing Generating | 2026 | 2025-03-31 | 2025 | Mar
Metering Test | T-4 | Proven DSR | 2026 | 2025-03-31 | 2025 | Mar
Metering Test | T-4 | Unproven DSR | 2026 | 2026-09-17 | 2026 | Sep
Metering Test | T-4 | Refurbishing | 2026 | 01/10/2027 (latest - provide by DY start to meet SCM) | 2027 | Oct
Metering Test | T-4 | Prospective Interconnector | 2026 | 01/10/2027 (latest - provide by DY start to meet SCM) | 2027 | Oct
Metering Test (With Multi-year Agreement) | T-4 | Unproven DSR | 2026 | 2027-09-17 | 2027 | Sep
Metering Test | T-1 | New Build | 2022 | 2022-10-01 | 2022 | Oct
Metering Test | T-1 | Existing Interconnector | 2022 | 2022-09-17 | 2022 | Sep
Metering Test | T-1 | Existing Generating | 2022 | 2022-09-17 | 2022 | Sep
Metering Test | T-1 | Proven DSR | 2022 | 2022-09-17 | 2022 | Sep
Metering Test | T-1 | Unproven DSR | 2022 | 2022-09-17 | 2022 | Sep
Metering Test | T-1 | Refurbishing | 2022 | 2022-10-01 | 2022 | Oct
Metering Test | T-1 | Prospective Interconnector | 2022 | 2022-10-01 | 2022 | Oct
Metering Test | T-1 | New Build | 2023 | 2023-10-01 | 2023 | Oct
Metering Test | T-1 | Existing Interconnector | 2023 | 2023-09-17 | 2023 | Sep
Metering Test | T-1 | Existing Generating | 2023 | 2023-09-17 | 2023 | Sep
Metering Test | T-1 | Proven DSR | 2023 | 2023-09-17 | 2023 | Sep
Metering Test | T-1 | Unproven DSR | 2023 | 2023-09-17 | 2023 | Sep
Metering Test | T-1 | Refurbishing | 2023 | 2023-10-01 | 2023 | Oct
Metering Test | T-1 | Prospective Interconnector | 2023 | 2023-10-01 | 2023 | Oct
Planning Consents | T-4 | New Build | 2025 | 2022-01-21 | 2022 | Jan
Planning Consents | T-1 | New Build | 2022 | 2022-01-14 | 2022 | Jan
Planning Consents | T-4 | Refurbishing | 2025 | 2022-01-21 | 2022 | Jan
Planning Consents | T-1 | Refurbishing | 2022 | 2022-01-14 | 2022 | Jan
Six monthly progress reporting date 10 | T-4 | New Build | 2021 | 2021-12-01 | 2021 | Dec
Six monthly progress reporting date 9 | T-4 | New Build | 2021 | 2021-06-01 | 2021 | Jun
Six monthly progress reporting date 11 | T-4 | New Build | 2021 | 2022-06-01 | 2022 | Jun
Six monthly progress reporting date 3 | T-3 | New Build | 2022 | 2021-06-01 | 2021 | Jun
Six monthly progress reporting date 4 | T-3 | New Build | 2022 | 2021-12-01 | 2021 | Dec
Six monthly progress reporting date 5 | T-3 | New Build | 2022 | 2022-06-01 | 2022 | Jun
Six monthly progress reporting date 6 | T-3 | New Build | 2022 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 7 | T-3 | New Build | 2022 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 6 | T-3 | Refurbishing | 2022 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 7 | T-3 | Refurbishing | 2022 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 3 | T-4 | New Build | 2023 | 2021-06-01 | 2021 | Jun
Six monthly progress reporting date 4 | T-4 | New Build | 2023 | 2021-12-01 | 2021 | Dec
Six monthly progress reporting date 5 | T-4 | New Build | 2023 | 2022-06-01 | 2022 | Jun
Six monthly progress reporting date 6 | T-4 | New Build | 2023 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 7 | T-4 | New Build | 2023 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 6 | T-4 | Refurbishing | 2023 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 7 | T-4 | Refurbishing | 2023 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 8 | T-4 | New Build | 2023 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 9 | T-4 | New Build | 2023 | 2024-06-01 | 2024 | Jun
Substantial Completion Milestone | T-1 | New Build | 2020 | 2020-10-01 | 2020 | Oct
Substantial Completion Milestone | T-1 | Refurbishing | 2020 | 2020-10-01 | 2020 | Oct
Substantial Completion Milestone | T-4 | New Build | 2020 | 2021-10-01 | 2021 | Oct
Substantial Completion Milestone | T-4 | Refurbishing | 2020 | 2021-10-01 | 2021 | Oct
Substantial Completion Milestone | T-1 | New Build | 2021 | 2021-10-01 | 2021 | Oct
Substantial Completion Milestone | T-1 | Refurbishing | 2021 | 2021-10-01 | 2021 | Oct
Substantial Completion Milestone | T-4 | New Build | 2021 | 2022-10-01 | 2022 | Oct
Substantial Completion Milestone | T-4 | Refurbishing | 2021 | 2022-10-01 | 2022 | Oct
Substantial Completion Milestone | T-1 | New Build | 2022 | 2022-10-01 | 2022 | Oct
Substantial Completion Milestone | T-1 | Refurbishing | 2022 | 2022-10-01 | 2022 | Oct
Substantial Completion Milestone | T-3 | New Build | 2022 | 2023-10-01 | 2023 | Oct
Substantial Completion Milestone | T-3 | Refurbishing | 2022 | 2023-10-01 | 2023 | Oct
Substantial Completion Milestone | T-4 | New Build | 2023 | 2024-10-01 | 2024 | Oct
Substantial Completion Milestone | T-4 | Refurbishing | 2023 | 2024-10-01 | 2024 | Oct
Substantial Completion Milestone | T-4 | New Build | 2024 | 2025-10-01 | 2025 | Oct
Substantial Completion Milestone | T-4 | Refurbishing | 2024 | 2025-10-01 | 2025 | Oct
Substantial Completion Milestone | T-4 | New Build | 2025 | 2026-10-01 | 2026 | Oct
Substantial Completion Milestone | T-4 | Refurbishing | 2025 | 2026-10-01 | 2026 | Oct
Substantial Completion Milestone | T-4 | New Build | 2026 | 2027-10-01 | 2027 | Oct
Substantial Completion Milestone | T-4 | Refurbishing | 2026 | 2027-10-01 | 2027 | Oct
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | New Build | 2020 | 2021-09-30 | 2021 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Existing Generating | 2020 | 2021-09-30 | 2021 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Proven DSR | 2020 | 2021-09-30 | 2021 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Unproven DSR | 2020 | 2021-09-30 | 2021 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Existing Interconnector | 2020 | 2021-09-30 | 2021 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Prospective Interconnector | 2020 | 2021-09-30 | 2021 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Refurbishing | 2020 | 2021-09-30 | 2021 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | New Build | 2021 | 2022-09-30 | 2022 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Existing Generating | 2021 | 2022-09-30 | 2022 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Proven DSR | 2021 | 2022-09-30 | 2022 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Unproven DSR | 2021 | 2022-09-30 | 2022 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Existing Interconnector | 2021 | 2022-09-30 | 2022 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Prospective Interconnector | 2021 | 2022-09-30 | 2022 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Refurbishing | 2021 | 2022-09-30 | 2022 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | New Build | 2022 | 2023-09-30 | 2023 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Existing Generating | 2022 | 2023-09-30 | 2023 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Proven DSR | 2022 | 2023-09-30 | 2023 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Unproven DSR | 2022 | 2023-09-30 | 2023 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Existing Interconnector | 2022 | 2023-09-30 | 2023 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Prospective Interconnector | 2022 | 2023-09-30 | 2023 | Sep
Suspend and recoup payments Satisfactory Performance Date (Auction 2016 and prior) | T-4 | Refurbishing | 2022 | 2023-09-30 | 2023 | Sep
Suspended Satisfactory Performance Date | T-1 | New Build | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Generating | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-1 | Proven DSR | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-1 | Unproven DSR | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Interconnector | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-1 | Prospective Interconnector | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-1 | Refurbishing | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-1 | New Build | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Generating | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-1 | Proven DSR | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-1 | Unproven DSR | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Interconnector | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-1 | Prospective Interconnector | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-1 | Refurbishing | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-1 | New Build | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Generating | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-1 | Proven DSR | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-1 | Unproven DSR | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Interconnector | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-1 | Prospective Interconnector | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-1 | Refurbishing | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-1 | New Build | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Generating | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-1 | Proven DSR | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-1 | Unproven DSR | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-1 | Existing Interconnector | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-1 | Prospective Interconnector | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-1 | Refurbishing | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-3 | New Build | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-3 | Existing Generating | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-3 | Proven DSR | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-3 | Unproven DSR | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-3 | Existing Interconnector | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-3 | Prospective Interconnector | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-3 | Refurbishing | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | New Build | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Generating | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-4 | Proven DSR | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-4 | Unproven DSR | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Interconnector | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-4 | Prospective Interconnector | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-4 | Refurbishing | 2020 | 2021-04-30 | 2021 | Apr
Suspended Satisfactory Performance Date | T-4 | New Build | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Generating | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-4 | Proven DSR | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-4 | Unproven DSR | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Interconnector | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-4 | Prospective Interconnector | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-4 | Refurbishing | 2021 | 2022-04-30 | 2022 | Apr
Suspended Satisfactory Performance Date | T-4 | New Build | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Generating | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | Proven DSR | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | Unproven DSR | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Interconnector | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | Prospective Interconnector | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | Refurbishing | 2022 | 2023-04-30 | 2023 | Apr
Suspended Satisfactory Performance Date | T-4 | New Build | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Generating | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-4 | Proven DSR | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-4 | Unproven DSR | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Interconnector | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-4 | Prospective Interconnector | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-4 | Refurbishing | 2023 | 2024-04-30 | 2024 | Apr
Suspended Satisfactory Performance Date | T-4 | New Build | 2024 | 2025-04-30 | 2025 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Generating | 2024 | 2025-04-30 | 2025 | Apr
Suspended Satisfactory Performance Date | T-4 | Proven DSR | 2024 | 2025-04-30 | 2025 | Apr
Suspended Satisfactory Performance Date | T-4 | Unproven DSR | 2024 | 2025-04-30 | 2025 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Interconnector | 2024 | 2025-04-30 | 2025 | Apr
Suspended Satisfactory Performance Date | T-4 | Prospective Interconnector | 2024 | 2025-04-30 | 2025 | Apr
Suspended Satisfactory Performance Date | T-4 | Refurbishing | 2024 | 2025-04-30 | 2025 | Apr
Suspended Satisfactory Performance Date | T-4 | New Build | 2025 | 2026-04-30 | 2026 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Generating | 2025 | 2026-04-30 | 2026 | Apr
Suspended Satisfactory Performance Date | T-4 | Proven DSR | 2025 | 2026-04-30 | 2026 | Apr
Suspended Satisfactory Performance Date | T-4 | Unproven DSR | 2025 | 2026-04-30 | 2026 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Interconnector | 2025 | 2026-04-30 | 2026 | Apr
Suspended Satisfactory Performance Date | T-4 | Prospective Interconnector | 2025 | 2026-04-30 | 2026 | Apr
Suspended Satisfactory Performance Date | T-4 | Refurbishing | 2025 | 2026-04-30 | 2026 | Apr
Suspended Satisfactory Performance Date | T-4 | New Build | 2026 | 2027-04-30 | 2027 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Generating | 2026 | 2027-04-30 | 2027 | Apr
Suspended Satisfactory Performance Date | T-4 | Proven DSR | 2026 | 2027-04-30 | 2027 | Apr
Suspended Satisfactory Performance Date | T-4 | Unproven DSR | 2026 | 2027-04-30 | 2027 | Apr
Suspended Satisfactory Performance Date | T-4 | Existing Interconnector | 2026 | 2027-04-30 | 2027 | Apr
Suspended Satisfactory Performance Date | T-4 | Prospective Interconnector | 2026 | 2027-04-30 | 2027 | Apr
Suspended Satisfactory Performance Date | T-4 | Refurbishing | 2026 | 2027-04-30 | 2027 | Apr
Terminated Satisfactory Performance Date | T-1 | New Build | 2020 | 2021-07-31 | 2021 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Generating | 2020 | 2021-07-31 | 2021 | Jul
Terminated Satisfactory Performance Date | T-1 | Proven DSR | 2020 | 2021-07-31 | 2021 | Jul
Terminated Satisfactory Performance Date | T-1 | Unproven DSR | 2020 | 2021-07-31 | 2021 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Interconnector | 2020 | 2021-07-31 | 2021 | Jul
Terminated Satisfactory Performance Date | T-1 | Prospective Interconnector | 2020 | 2021-07-31 | 2021 | Jul
Terminated Satisfactory Performance Date | T-1 | Refurbishing | 2020 | 2021-07-31 | 2021 | Jul
Terminated Satisfactory Performance Date | T-1 | New Build | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Generating | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-1 | Proven DSR | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-1 | Unproven DSR | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Interconnector | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-1 | Prospective Interconnector | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-1 | Refurbishing | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-1 | New Build | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Generating | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-1 | Proven DSR | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-1 | Unproven DSR | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Interconnector | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-1 | Prospective Interconnector | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-1 | Refurbishing | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-1 | New Build | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Generating | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-1 | Proven DSR | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-1 | Unproven DSR | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Interconnector | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-1 | Prospective Interconnector | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-1 | Refurbishing | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-1 | New Build | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Generating | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-1 | Proven DSR | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-1 | Unproven DSR | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Interconnector | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-1 | Prospective Interconnector | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-1 | Refurbishing | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-1 | New Build | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Generating | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-1 | Proven DSR | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-1 | Unproven DSR | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-1 | Existing Interconnector | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-1 | Prospective Interconnector | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-1 | Refurbishing | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-3 | New Build | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-3 | Existing Generating | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-3 | Proven DSR | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-3 | Unproven DSR | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-3 | Existing Interconnector | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-3 | Prospective Interconnector | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-3 | Refurbishing | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | New Build | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Generating | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-4 | Proven DSR | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-4 | Unproven DSR | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Interconnector | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-4 | Prospective Interconnector | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-4 | Refurbishing | 2021 | 2022-07-31 | 2022 | Jul
Terminated Satisfactory Performance Date | T-4 | New Build | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Generating | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | Proven DSR | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | Unproven DSR | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Interconnector | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | Prospective Interconnector | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | Refurbishing | 2022 | 2023-07-31 | 2023 | Jul
Terminated Satisfactory Performance Date | T-4 | New Build | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Generating | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-4 | Proven DSR | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-4 | Unproven DSR | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Interconnector | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-4 | Prospective Interconnector | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-4 | Refurbishing | 2023 | 2024-07-31 | 2024 | Jul
Terminated Satisfactory Performance Date | T-4 | New Build | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Generating | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-4 | Proven DSR | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-4 | Unproven DSR | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Interconnector | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-4 | Prospective Interconnector | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-4 | Refurbishing | 2024 | 2025-07-31 | 2025 | Jul
Terminated Satisfactory Performance Date | T-4 | New Build | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Generating | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-4 | Proven DSR | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-4 | Unproven DSR | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Interconnector | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-4 | Prospective Interconnector | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-4 | Refurbishing | 2025 | 2026-07-31 | 2026 | Jul
Terminated Satisfactory Performance Date | T-4 | New Build | 2026 | 2027-07-31 | 2027 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Generating | 2026 | 2027-07-31 | 2027 | Jul
Terminated Satisfactory Performance Date | T-4 | Proven DSR | 2026 | 2027-07-31 | 2027 | Jul
Terminated Satisfactory Performance Date | T-4 | Unproven DSR | 2026 | 2027-07-31 | 2027 | Jul
Terminated Satisfactory Performance Date | T-4 | Existing Interconnector | 2026 | 2027-07-31 | 2027 | Jul
Terminated Satisfactory Performance Date | T-4 | Prospective Interconnector | 2026 | 2027-07-31 | 2027 | Jul
Terminated Satisfactory Performance Date | T-4 | Refurbishing | 2026 | 2027-07-31 | 2027 | Jul
Total Project Spend | T-3 | New Build | 2022 | 2023-01-01 | 2023 | Jan
Total Project Spend | T-3 | Unproven DSR | 2022 | 2023-01-01 | 2023 | Jan
Total Project Spend | T-3 | Refurbishing | 2022 | 2023-01-01 | 2023 | Jan
Total Project Spend | T-4 | New Build | 2020 | 2021-01-01 | 2021 | Jan
Total Project Spend | T-4 | Unproven DSR | 2020 | 2021-01-01 | 2021 | Jan
Total Project Spend | T-4 | Refurbishing | 2020 | 2021-01-01 | 2021 | Jan
Total Project Spend | T-4 | New Build | 2021 | 2022-01-01 | 2022 | Jan
Total Project Spend | T-4 | Unproven DSR | 2021 | 2022-01-01 | 2022 | Jan
Total Project Spend | T-4 | Refurbishing | 2021 | 2022-01-01 | 2022 | Jan
Total Project Spend | T-4 | New Build | 2023 | 2024-01-01 | 2024 | Jan
Total Project Spend | T-4 | Unproven DSR | 2023 | 2024-01-01 | 2024 | Jan
Total Project Spend | T-4 | Refurbishing | 2023 | 2024-01-01 | 2024 | Jan
Total Project Spend | T-4 | New Build | 2024 | 2025-01-01 | 2025 | Jan
Total Project Spend | T-4 | Unproven DSR | 2024 | 2025-01-01 | 2025 | Jan
Total Project Spend | T-4 | Refurbishing | 2024 | 2025-01-01 | 2025 | Jan
Total Project Spend | T-4 | New Build | 2025 | 2026-01-01 | 2026 | Jan
Total Project Spend | T-4 | Unproven DSR | 2025 | 2026-01-01 | 2026 | Jan
Total Project Spend | T-4 | Refurbishing | 2025 | 2026-01-01 | 2026 | Jan
Total Project Spend | T-4 | New Build | 2026 | 2027-01-01 | 2027 | Jan
Total Project Spend | T-4 | Refurbishing | 2026 | 2027-01-01 | 2027 | Jan
Total Project Spend | T-4 | Unproven DSR | 2026 | 2027-01-01 | 2027 | Jan
Six monthly progress reporting date 8 | T-4 | Refurbishing | 2023 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 9 | T-4 | Refurbishing | 2023 | 2024-06-01 | 2024 | Jun
Six monthly progress reporting date 1 | T-4 | New Build | 2024 | 2021-06-01 | 2021 | Jun
Six monthly progress reporting date 2 | T-4 | New Build | 2024 | 2021-12-01 | 2021 | Dec
Six monthly progress reporting date 3 | T-4 | New Build | 2024 | 2022-06-01 | 2022 | Jun
Six monthly progress reporting date 4 | T-4 | New Build | 2024 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 5 | T-4 | New Build | 2024 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 6 | T-4 | New Build | 2024 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 7 | T-4 | New Build | 2024 | 2024-06-01 | 2024 | Jun
Six monthly progress reporting date 8 | T-4 | New Build | 2024 | 2024-12-01 | 2024 | Dec
Six monthly progress reporting date 9 | T-4 | New Build | 2024 | 2025-06-01 | 2025 | Jun
Six monthly progress reporting date 4 | T-4 | Refurbishing | 2024 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 5 | T-4 | Refurbishing | 2024 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 6 | T-4 | Refurbishing | 2024 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 7 | T-4 | Refurbishing | 2024 | 2024-06-01 | 2024 | Jun
Six monthly progress reporting date 8 | T-4 | Refurbishing | 2024 | 2024-12-01 | 2024 | Dec
Six monthly progress reporting date 9 | T-4 | Refurbishing | 2024 | 2025-06-01 | 2025 | Jun
Six monthly progress reporting date 1 | T-4 | New Build | 2025 | 2022-06-01 | 2022 | Jun
Six monthly progress reporting date 2 | T-4 | New Build | 2025 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 3 | T-4 | New Build | 2025 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 4 | T-4 | New Build | 2025 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 5 | T-4 | New Build | 2025 | 2024-06-01 | 2024 | Jun
Six monthly progress reporting date 6 | T-4 | New Build | 2025 | 2024-12-01 | 2024 | Dec
Six monthly progress reporting date 7 | T-4 | New Build | 2025 | 2025-06-01 | 2025 | Jun
Six monthly progress reporting date 8 | T-4 | New Build | 2025 | 2025-12-01 | 2025 | Dec
Six monthly progress reporting date 9 | T-4 | New Build | 2025 | 2026-06-01 | 2026 | Jun
Six monthly progress reporting date 1 | T-4 | Refurbishing | 2025 | 2022-06-01 | 2022 | Jun
Six monthly progress reporting date 2 | T-4 | Refurbishing | 2025 | 2022-12-01 | 2022 | Dec
Six monthly progress reporting date 3 | T-4 | Refurbishing | 2025 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 4 | T-4 | Refurbishing | 2025 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 5 | T-4 | Refurbishing | 2025 | 2024-06-01 | 2024 | Jun
Six monthly progress reporting date 6 | T-4 | Refurbishing | 2025 | 2024-12-01 | 2024 | Dec
Six monthly progress reporting date 7 | T-4 | Refurbishing | 2025 | 2025-06-01 | 2025 | Jun
Six monthly progress reporting date 8 | T-4 | Refurbishing | 2025 | 2025-12-01 | 2025 | Dec
Six monthly progress reporting date 9 | T-4 | Refurbishing | 2025 | 2026-06-01 | 2026 | Jun
Six monthly progress reporting date 1 | T-4 | New Build | 2026 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 2 | T-4 | New Build | 2026 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 3 | T-4 | New Build | 2026 | 2024-06-01 | 2024 | Jun
Six monthly progress reporting date 4 | T-4 | New Build | 2026 | 2024-12-01 | 2024 | Dec
Six monthly progress reporting date 5 | T-4 | New Build | 2026 | 2025-06-01 | 2025 | Jun
Six monthly progress reporting date 6 | T-4 | New Build | 2026 | 2025-12-01 | 2025 | Dec
Six monthly progress reporting date 7 | T-4 | New Build | 2026 | 2026-06-01 | 2026 | Jun
Six monthly progress reporting date 8 | T-4 | New Build | 2026 | 2026-12-01 | 2026 | Dec
Six monthly progress reporting date 9 | T-4 | New Build | 2026 | 2027-06-01 | 2027 | Jun
Six monthly progress reporting date 1 | T-4 | Refurbishing | 2026 | 2023-06-01 | 2023 | Jun
Six monthly progress reporting date 2 | T-4 | Refurbishing | 2026 | 2023-12-01 | 2023 | Dec
Six monthly progress reporting date 3 | T-4 | Refurbishing | 2026 | 2024-06-01 | 2024 | Jun
Six monthly progress reporting date 4 | T-4 | Refurbishing | 2026 | 2024-12-01 | 2024 | Dec
Six monthly progress reporting date 5 | T-4 | Refurbishing | 2026 | 2025-06-01 | 2025 | Jun
Six monthly progress reporting date 6 | T-4 | Refurbishing | 2026 | 2025-12-01 | 2025 | Dec
Six monthly progress reporting date 7 | T-4 | Refurbishing | 2026 | 2026-06-01 | 2026 | Jun
Six monthly progress reporting date 8 | T-4 | Refurbishing | 2026 | 2026-12-01 | 2026 | Dec
Six monthly progress reporting date 9 | T-4 | Refurbishing | 2026 | 2027-06-01 | 2027 | Jun
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel.
If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Coronavirus Easements
1) Extended Long-Stop Date
Deadline Name | Auction type | Generating CMU Type | Delivery Year | Deadline Date | Year of deadline | Month of deadline
Substantial Completion Milestone | T-4 | New Build | 2021 | 2022-09-30 | 2022 | Sep
Substantial Completion Milestone | T-4 | New Build | 2019 | 2022-09-30 | 2022 | Sep
Substantial Completion Milestone | T-4 | Refurbishing | 2020 | 2022-09-30 | 2022 | Sep
2.) Extended DSR Test or Metering Test
Deadline Name | Auction type | Generating CMU Type | Delivery Year | Deadline Date | Year of deadline | Month of deadline
Metering Test | T-1 | Unproven DSR | 2020 | 2022-09-17 | 2022 | Sep
DSR Test | T-4 | Unproven DSR | 2020 | 2022-08-31 | 2022 | Aug
DSR Test | T-1 | Unproven DSR | 2020 | 2022-08-31 | 2022 | Aug
Modifications in Respect of the Effects of Coronavirus (CM Rules Chapter 18)
1.) Extended Long-Stop Date
! Please note, the following deadlines are conditional based on meeting the eligibility requirements described in Rule 6.7.4A within Chapter 18 of the Capacity Market Rules. They are only applicable to those CMUs that have received Delivery Body approval following submission of an ITE report by September 30th 2021. Those with a 2015 (T-4) Agreement will automatically have their Longstop date extended to the 30 September 2022 providing an ITE report was provided and approved before the 30 September 2020.
2.) Extended DSR Test or Metering Test
! Please note, the following deadlines are conditional based on meeting the eligibility requirements described in Rule 8.3.2ZA within Chapter 18 of the Capacity Market Rules. They are only applicable to those CMUs that have received Delivery Body approval following submission of an ITE report by August 31st 2022.